## Full 1
id | ref | subject | description | sprint_id | sprint | sprint_estimated_start | sprint_estimated_finish | owner | owner_full_name | assigned_to | assigned_to_full_name | assigned_users | assigned_users_full_name | status | is_closed | back-points | design-points | front-points | ux-points | total-points | backlog_order | sprint_order | kanban_order | created_date | modified_date | finish_date | client_requirement | team_requirement | attachments | generated_from_issue | generated_from_task | from_task_ref | external_reference | tasks | tags | watchers | voters | due_date | due_date_reason | relation_point-hour | relation_hour-price | Costs
3427688 | 3 | Prepare Final Presentation |  | 275649 | Sprint 13 | 2020-12-15 | 2020-12-21 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | Done | TRUE |  | 8.0 |  |  | 8 | 1602503799410 | 1 | 1602503799409 | 2020-10-12 11:56:39.434668+00:00 | 2020-10-12 12:02:56.924501+00:00 | 2020-09-28 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | docs | [] | 0 |  |  | 4 | 10 | 320
3427690 | 4 | Test results and conclusions |  | 275648 | Sprint 12 | 2020-12-08 | 2020-12-14 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 8.0 |  |  | 8 | 1602503799411 | 1 | 1602503830360 | 2020-10-12 11:57:10.384747+00:00 | 2020-10-12 12:02:01.521759+00:00 | 2020-10-05 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | docs | [] | 0 |  |  | 4 | 10 | 320
3427691 | 5 | Implement solution |  | 275647 | Sprint 11 | 2020-12-01 | 2020-12-07 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | In progress | FALSE |  | 8.0 |  |  | 8 | 1602503799412 | 1 | 1602503861897 | 2020-10-12 11:57:41.925329+00:00 | 2020-10-12 12:01:09.983456+00:00 | 2020-10-12 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | docs | [] | 0 |  |  | 4 | 10 | 320
3427693 | 6 | Prepare tools for justification of solution | Make tools that help demonstrate the solution works. | 275646 | Sprint 10 | 2020-11-24 | 2020-11-30 | ismaeldlg | Ismael de la Gracia Cobos |  |  |  |  | New | FALSE |  | 8.0 |  |  | 8 | 1602503985829 | 2 | 1602503985829 | 2020-10-12 11:59:45.853505+00:00 | 2020-10-12 15:11:52.482069+00:00 | 2020-10-19 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | docs | [] | 0 |  |  | 4 | 10 | 320
3427932 | 7 | Research on how to make the solution cross-platform |  | 275645 | Sprint 9 | 2020-11-17 | 2020-11-23 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 13.0 |  |  | 13 | 1602515266053 | 1 | 1602515266053 | 2020-10-12 15:07:46.071509+00:00 | 2020-10-12 15:15:32.978500+00:00 | 2020-10-19 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | code | [] | 0 |  |  | 4 | 10 | 520
3427935 | 9 | Design a unique solution |  | 275644 | Sprint 8 | 2020-11-10 | 2020-11-16 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 13.0 |  |  | 13 | 1602515439917 | 1 | 1602515439912 | 2020-10-12 15:10:39.936627+00:00 | 2020-10-12 15:16:01.375419+00:00 | 2020-10-26 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research,code | [] | 0 |  |  | 4 | 10 | 520
3427934 | 8 | Apply solution to in-browser and full VPNs |  | 275640 | Sprint 7 | 2020-11-03 | 2020-11-09 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 20.0 |  |  | 20 | 1602515439918 | 1 | 1602515334040 | 2020-10-12 15:08:54.056889+00:00 | 2020-10-12 15:16:04.680912+00:00 | 2020-11-02 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research,code | [] | 0 |  |  | 4 | 10 | 800
3427937 | 10 | TLS Interception | Find a way to detect TLS interception performed by a VPN. | 275638 | Sprint 6 | 2020-10-27 | 2020-11-02 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 20.0 |  |  | 20 | 1602515839091 | 1 | 1602515839090 | 2020-10-12 15:17:19.122812+00:00 | 2020-10-12 15:24:34.903956+00:00 | 2020-11-09 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research,code,docs | [] | 0 |  |  | 4 | 10 | 800
3427942 | 12 | Traffic redirection | Research on traffic redirection and how a VPN can do it. Detect traffic redirection. | 275637 | Sprint 5 | 2020-10-20 | 2020-10-26 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 40.0 |  |  | 13 | 0 | 0 | 1602516307284 | 2020-10-12 15:25:07.311477+00:00 | 2020-10-12 15:28:12.899636+00:00 | 2020-11-16 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research,code | [] | 0 |  |  | 4 | 10 | 520
3427943 | 13 | JS Injection | Detect JS Injection performed by a VPN using a controlled environment (browser/OS with certain VPN installed) and making requests with the VPN working and off. Analyze webpages, looking for JS injection the VPN might have made, specially advertising one. | 275636 | Sprint 4 | 2020-10-13 | 2020-10-19 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 13.0 |  |  | 13 | 1602516417959 | 0 | 1602516417959 | 2020-10-12 15:26:57.983355+00:00 | 2020-10-12 15:28:18.156315+00:00 | 2020-11-23 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research | [] | 0 |  |  | 4 | 10 | 520
3427945 | 14 | Deliverable 4 | Final written document summarising the project. This document brings together deliverables 1, 2 and 3 and takes into account the lecturers’ feedback. It cannot be longer than 30 pages. | 275636 | Sprint 4 | 2020-10-13 | 2020-10-19 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 20.0 |  |  | 20 | 1602516472436 | 0 | 1602516472436 | 2020-10-12 15:27:52.463769+00:00 | 2020-10-12 15:28:23.348129+00:00 | 2020-11-30 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | code,research | [] | 0 |  |  | 4 | 10 | 800
3427947 | 15 | Deliverable 3 | The deliverable begins with a self-assessment on sustainability, which you can summarize in 300 words once replied the survey in goo.gl/kWLMLE. The next section would be an analysis of the sustainability of the project, based on the sustainability matrix contained in figure 3-– TFG’s sustainability matrix questions (I: initial milestone, F:final milestone) -– of the document "Module 2.6 Sustainability report.pdf."When dealing with the economic dimension of this report, it is necessary to make a budget (criterion "Budget" in the rubric) of the project (according to the criteria: “Task Description”,”Estimation and Gantt”, and “Management control”); and then write an assessment according to the "Reflection" criterion. The rest of the dimensions of the sustainability report shall be developed directly based on (textually) answers to the questions in the "Reflection" criterion of the rubric. Please, give answer to the questions of the table. The document cannot have an extension of more than 5 pages. | 275605 | Sprint 3 | 2020-10-06 | 2020-10-12 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 40.0 |  |  | 20 | 1602516520467 | 0 | 1602516520467 | 2020-10-12 15:28:40.492001+00:00 | 2020-10-12 15:28:47.823130+00:00 | 2020-12-07 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | code | [] | 0 |  |  | 4 | 10 | 800
3427948 | 16 | Deliverable 2 | Planning of the entire execution of the TFG. Students should provide a description of the project phases, and the resources and requirements associated with each one. Some of the scheduling tools described in the module should be used. The document can be no longer than 5 pages. | 275607 | Sprint 2 | 2020-09-29 | 2020-10-05 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 20.0 |  |  | 20 | 1602516557325 | 0 | 1602516557325 | 2020-10-12 15:29:17.350384+00:00 | 2020-10-12 15:29:22.108452+00:00 | 2020-12-14 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | research,docs | [] | 0 |  |  | 4 | 10 | 800
3427939 | 11 | Deliverable 1 | Definition of the scope of the project in the context of its study. You must indicate the general objective of the TFG, the context, the reason for selecting the subject area (relevance and justification), how the project will be developed and using which means. The document can be no longer than 10 pages. | 275608 | Sprint 1 | 2020-09-22 | 2020-09-28 | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | ismaeldlg | Ismael de la Gracia Cobos | New | FALSE |  | 13.0 |  |  | 13 | 1602516215915 | 1 | 1602516215914 | 2020-10-12 15:23:35.938471+00:00 | 2020-10-12 15:23:45.938485+00:00 | 2020-12-21 23:59:59+00:00 | FALSE | FALSE | 0 | [5 empty] | docs | [] | 0 |  |  | 4 | 10 | 520
[6 empty] | Total | [13 empty] | 197 | 20832659553143 | 10 | 22435175847975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 7880

## Full 2
Subject | Sprint Start | Sprint Finish | Point/Hour | Hour/€ |  | Total Point | Total Hours (h) | Wage/h | Total CPA | Total GC | Comments | Total Incidental | Comments
Prepare Final Presentation | 2020-12-15 | 2020-12-21 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 8 | 32 | 10 | 320 | 0.050458 | Electricity RPI ( 0.51 Wh * Total hours * Electricity_Cost (0,125555 €/kwh)) | 80 | We need more raspberries for time reason
Test results and conclusions | 2020-12-08 | 2020-12-14 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 8 | 32 | 10 | 320 | 39.5749 | Electricity Development (400W * Total hours * Electricity_Cost (0,125555 €/kwh)) | 100 | We may need to pay for some VPNs to test
Implement solution | 2020-12-01 | 2020-12-07 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 8 | 32 | 10 | 320 | 40 | Buy Raspberry Kit | 0
Prepare tools for justification of solution | 2020-11-24 | 2020-11-30 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 8 | 32 | 10 | 320 | 0 |  | 0
Research on how to make the solution cross-platform | 2020-11-17 | 2020-11-23 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 13 | 52 | 10 | 520 | 0 |  | 0
Design a unique solution | 2020-11-10 | 2020-11-16 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 13 | 52 | 10 | 520 | 0 |  | 0
Apply solution to in-browser and full VPNs | 2020-11-03 | 2020-11-09 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 20 | 80 | 10 | 800 | 0 |  | 0
TLS Interception | 2020-10-27 | 2020-11-02 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 20 | 80 | 10 | 800 | 0 |  | 0
Traffic redirection | 2020-10-20 | 2020-10-26 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 13 | 52 | 10 | 520 | 0 |  | 0
JS Injection | 2020-10-13 | 2020-10-19 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 13 | 52 | 10 | 520 | 0 |  | 0
Deliverable 4 | 2020-10-13 | 2020-10-19 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 20 | 80 | 10 | 800 | 0 |  | 0
Deliverable 3 | 2020-10-06 | 2020-10-12 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 20 | 80 | 10 | 800 | 0 |  | 0
Deliverable 2 | 2020-09-29 | 2020-10-05 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 20 | 80 | 10 | 800 | 0 |  | 0
Deliverable 1 | 2020-09-22 | 2020-09-28 | 4 | 10 | Internship wage goes around 10€/h on average, and the developer is a student | 13 | 52 | 10 | 520 | 0 |  | 0
[5 empty] | Totals | 197 | 788 | 140 | 7880 | 79.6254 | Contingency: 20% | 180 | TOTAL COSTS | 9731.5505